Project schedule

 2022/2023

|  |  |  |  |
| --- | --- | --- | --- |
|  Activities |  Deadlines |  Responsible |  Notes |
| Online meeting of project coordinators |  15.03.2022 |  Bulgaria | Discussing the start of the project |
| Conflict management plan |  15.03.2022 |  all partners | Preparation and agreements |
| Risk management plan |  15.03.2022 |  | Preparation and agreements |
| Project dissemination | throughout of the project period |  all partners | Products: posters and board displays; social networks and media publications, etc. |
| Pre-surveys about STEAM for students and teachers |  31.03.2022 |  Bulgaria | Mentimeter;Surveymonkey.comProducts: a video and a report |
| Logo creation and voting |  30.04.2022 |  all partners | Canva and Mentimeter |
| Presenting the project objectives and activities to the participants |  30.04.2022 |  all partners | to students, teachers and parents (both in person and online possible) |
| Presenting the results of pre-surveys and reports |  30.04.2022 |  all partners | to students, teachers and parents (both in person and online possible) |
| Logo winner announcement and presenting the results |  1.05.2022 |  Bulgaria | Voki.com and a report |
| Project social networks profiles |  31.05.2022 |  all partners | according to the agreed tasks and responsibilities |
| Erasmus + corners  |  31.05.2022 |  all partners | Posters, brochures,etc. |
| Science and Technology Club |  31.05.2022 |  all partners | Science and Technology Club Annual Plan |
| Online meeting of coordinators |  15.06.2022 |  Bulgaria | Discussion of the mobilities dates’ changes  |
| “The motion of technology” activity at school |  15.06.2022 |  all partners | Preparation for the mobility |
| Students’ Portfolios |  30.06.2022 |  all partners | on paper |
| Audit  |  30.06. 2022 |  Bulgaria | 6th month audit of the project results |
| Project website creation |  30.07.2022 |  Serbia | Weebly.com |
| Selection criteria process |  15.08.2022 |  Bulgaria/Serbia | Tests/interviews |
| Summer dissemination campaign |  31.08.2022 |  all partners | Formal and informal individually and in teams meetings and seminarsSurveys and analysis. |
| Online meeting of coordinators |  31.08.2022 |  Bulgaria | Discussing the upcoming mobility in Turkiye |
| Creation of the project e-calendar |   31.08. 2022 |   Bulgaria | Trello.com |
| First mobility in Turkiye“The motion of the technology” |  19th-23rd September |  Turkiye | Held according to the form in the applying stage |
| Evaluation sheets/online evaluation |  31.09.2022 |  Turkiye/Bulgaria | during and after the mobilityfollow-up lists/Portfolios |
| eTwinning project creation |  31.09.2022 |  Turkiye/Serbia | Postponed to November 2022 |
| Online meeting of coordinators |  01.10.2022 |  Bulgaria | Discussing the upcoming virtual mobility in Serbia |
| “Art in everywhere” at school |  16. 10.2022 |  all partners | Preparation of the virtual mobility |
| Erasmus Days 2022 |  13th-15th October 2022 |  all partners | Celebration-photos, round tables,etc. |
| First virtual mobility in Serbia“Art in everywhere” |  17th-28th October 2022 |  Serbia | as many participants as possible via zoom |
| Photography contest “Golden ratio seen in the nature” |  21st-25th October 2022 |  all partners | Photos, mentimeter voting, report |
| Online evaluation of the mobility |  30.10.2022 |  Serbia/Bulgaria | during and after the mobilityfollow-up lists/Portfolios |
| Creation of e-journal |  30.10.2022 |  Turkiye | Emaze.com |
| Online meeting of coordinators |  30. 10. 2022 |  Bulgaria | Discussing the Interim report and dissemination |
| Creating “Art in everywhere” online gallery |  15.11.2022 |  Bulgaria | Photos with artworks of students of three different countries |
| Interim evaluation of students’ and teachers’ progress and project success |  15.11.2022 |   all partners | surveymonkey.com |
| Writing the Interim report |  31.11.2022 |  Bulgaria | To be sent to Bulgarian NA by 31.11.2022 |
| Etwinning project creation |  31.11.2022 |  Turkiye/Serbia | Started in November 2022 |
| Interim Multiplier events |  31.12.2022 |  all partners | Dissemination of the results of the project so far |
| Coordinators’ meeting |  31.12.2022 |  Bulgaria  | Discussing the virtual mobility in Turkiye |
| “Our world is a machine” activities at school |  31.01.2023 |  all partners | Preparation of the virtual mobility in Turkiye |
| Second virtual mobility “Our world is a machine” in Turkey |  04.04-18.01.2023 |  Turkiye | as many participants as possible via zoom |
| ICT contest “Moving ladybird” |  16.01-18.01.2023 |  all partners | Photos, surveymonkey voting, report |
| Online evaluation of the meeting |  31.01.2023 |  Turkiye/Bulgaria | during and after the meeting |
| Coordinators’ meeting |  28.02.2023 |  Bulgaria | Discussing the upcoming mobility in Bulgaria |
| “Ready or not, here I come Math” activities at school |  28.02.2023 |  Bulgaria  | Preparation of the mobility |
| Selection criteria process |  28.02.2023 |  Serbia/Turkiye | Tests/interviews |
| Online meeting of coordinators |  04.03.2023 |  Bulgaria | Discussing the upcoming mobility in Bulgaria |
| “Ready or not, here I come Math” in Bulgaria |  27.03-31.03.2023 |  Bulgaria | Held according to the form in the applying stage |
| Evaluation of the mobility |  31.03.2023 |  Turkiye/Bulgaria | during and after the mobility |
| “Science in the nature” activities at school |  30.04.2023 |  all partners | Preparation of the mobility in Serbia |
| Selection criteria process |  30.04.2023 |  Bulgaria/Turkiye | Tests/interviews |
| Online meeting of coordinators |  30.04.2023 |  Bulgaria | Discussing the upcoming mobility in Serbia |
| “Science in the nature” in Serbia |  24th-28th 2023  |  Serbia | Held according to the form in the applying stage |
| Evaluation of the mobility |  30.05.2023 |  Serbia/Bulgaria | during and after the mobility |
| Final Multiplier event |  26.06.2023 |  Bulgaria | Presenting the project to wider community |
| Eco-friendly activities at school | throughout of the project period |  all partners | during the mobilities |
| Evaluation of the project results |  30.06.2023 |  all partners | reports |
| Writing a collaborative paperbook |  30.06.2023 |  all partners | final product |
| Online meeting of the coordinators |  30.06.2023 |  Bulgaria | Discussing the project results, the final report and dissemination |
| Writing the final report  |  31.07.2023 |  Serbia/Turkiye | To be sent to Bulgarian coordinator |
| Writing the final report |  31.08.2023 |  Bulgaria | To be sent to Bulgarian NA |