Project schedule

2022/2023

|  |  |  |  |
| --- | --- | --- | --- |
| Activities | Deadlines | Responsible | Notes |
| Online meeting of project coordinators | 15.03.2022 | Bulgaria | Discussing the start of the project |
| Conflict management plan | 15.03.2022 | all partners | Preparation and agreements |
| Risk management plan | 15.03.2022 |  | Preparation and agreements |
| Project dissemination | throughout of the project period | all partners | Products: posters and board displays; social networks and media publications, etc. |
| Pre-surveys about STEAM for students and teachers | 31.03.2022 | Bulgaria | Mentimeter;Surveymonkey.com  Products: a video and a report |
| Logo creation and voting | 30.04.2022 | all partners | Canva and Mentimeter |
| Presenting the project objectives and activities to the participants | 30.04.2022 | all partners | to students, teachers and parents (both in person and online possible) |
| Presenting the results of pre-surveys and reports | 30.04.2022 | all partners | to students, teachers and parents (both in person and online possible) |
| Logo winner announcement and presenting the results | 1.05.2022 | Bulgaria | Voki.com and a report |
| Project social networks profiles | 31.05.2022 | all partners | according to the agreed tasks and responsibilities |
| Erasmus + corners | 31.05.2022 | all partners | Posters, brochures,etc. |
| Science and Technology Club | 31.05.2022 | all partners | Science and Technology Club Annual Plan |
| Online meeting of coordinators | 15.06.2022 | Bulgaria | Discussion of the mobilities dates’ changes |
| “The motion of technology” activity at school | 15.06.2022 | all partners | Preparation for the mobility |
| Students’ Portfolios | 30.06.2022 | all partners | on paper |
| Audit | 30.06. 2022 | Bulgaria | 6th month audit of the project results |
| Project website creation | 30.07.2022 | Serbia | Weebly.com |
| Selection criteria process | 15.08.2022 | Bulgaria/Serbia | Tests/interviews |
| Summer dissemination campaign | 31.08.2022 | all partners | Formal and informal individually and in teams meetings and seminars  Surveys and analysis. |
| Online meeting of coordinators | 31.08.2022 | Bulgaria | Discussing the upcoming mobility in Turkiye |
| Creation of the project e-calendar | 31.08. 2022 | Bulgaria | Trello.com |
| First mobility in Turkiye  “The motion of the technology” | 19th-23rd September | Turkiye | Held according to the form in the applying stage |
| Evaluation sheets/online evaluation | 31.09.2022 | Turkiye/Bulgaria | during and after the mobility  follow-up lists/Portfolios |
| eTwinning project creation | 31.09.2022 | Turkiye/Serbia | Postponed to November 2022 |
| Online meeting of coordinators | 01.10.2022 | Bulgaria | Discussing the upcoming virtual mobility in Serbia |
| “Art in everywhere” at school | 16. 10.2022 | all partners | Preparation of the virtual mobility |
| Erasmus Days 2022 | 13th-15th October 2022 | all partners | Celebration-photos, round tables,etc. |
| First virtual mobility in Serbia  “Art in everywhere” | 17th-28th October 2022 | Serbia | as many participants as possible via zoom |
| Photography contest “Golden ratio seen in the nature” | 21st-25th October 2022 | all partners | Photos, mentimeter voting, report |
| Online evaluation of the mobility | 30.10.2022 | Serbia/Bulgaria | during and after the mobility  follow-up lists/Portfolios |
| Creation of e-journal | 30.10.2022 | Turkiye | Emaze.com |
| Online meeting of coordinators | 30. 10. 2022 | Bulgaria | Discussing the Interim report and dissemination |
| Creating “Art in everywhere” online gallery | 15.11.2022 | Bulgaria | Photos with artworks of students of three different countries |
| Interim evaluation of students’ and teachers’ progress and project success | 15.11.2022 | all partners | surveymonkey.com |
| Writing the Interim report | 31.11.2022 | Bulgaria | To be sent to Bulgarian NA  by 31.11.2022 |
| Etwinning project creation | 31.11.2022 | Turkiye/Serbia | Started in November 2022 |
| Interim Multiplier events | 31.12.2022 | all partners | Dissemination of the results of the project so far |
| Coordinators’ meeting | 31.12.2022 | Bulgaria | Discussing the virtual mobility in Turkiye |
| “Our world is a machine” activities at school | 31.01.2023 | all partners | Preparation of the virtual mobility in Turkiye |
| Second virtual mobility “Our world is a machine” in Turkey | 04.04-18.01.2023 | Turkiye | as many participants as possible via zoom |
| ICT contest “Moving ladybird” | 16.01-18.01.2023 | all partners | Photos, surveymonkey voting, report |
| Online evaluation of the meeting | 31.01.2023 | Turkiye/Bulgaria | during and after the meeting |
| Coordinators’ meeting | 28.02.2023 | Bulgaria | Discussing the upcoming mobility in Bulgaria |
| “Ready or not, here I come Math” activities at school | 28.02.2023 | Bulgaria | Preparation of the mobility |
| Selection criteria process | 28.02.2023 | Serbia/Turkiye | Tests/interviews |
| Online meeting of coordinators | 04.03.2023 | Bulgaria | Discussing the upcoming mobility in Bulgaria |
| “Ready or not, here I come Math” in Bulgaria | 27.03-31.03.2023 | Bulgaria | Held according to the form in the applying stage |
| Evaluation of the mobility | 31.03.2023 | Turkiye/Bulgaria | during and after the mobility |
| “Science in the nature” activities at school | 30.04.2023 | all partners | Preparation of the mobility in Serbia |
| Selection criteria process | 30.04.2023 | Bulgaria/Turkiye | Tests/interviews |
| Online meeting of coordinators | 30.04.2023 | Bulgaria | Discussing the upcoming mobility in Serbia |
| “Science in the nature” in Serbia | 24th-28th 2023 | Serbia | Held according to the form in the applying stage |
| Evaluation of the mobility | 30.05.2023 | Serbia/Bulgaria | during and after the mobility |
| Final Multiplier event | 26.06.2023 | Bulgaria | Presenting the project to wider community |
| Eco-friendly activities at school | throughout of the project period | all partners | during the mobilities |
| Evaluation of the project results | 30.06.2023 | all partners | reports |
| Writing a collaborative paperbook | 30.06.2023 | all partners | final product |
| Online meeting of the coordinators | 30.06.2023 | Bulgaria | Discussing the project results, the final report and dissemination |
| Writing the final report | 31.07.2023 | Serbia/Turkiye | To be sent to Bulgarian coordinator |
| Writing the final report | 31.08.2023 | Bulgaria | To be sent to Bulgarian NA |